## Definations
Term | Defination/ Description
Expert Judgement
Data Gathering
Brainstorming
Focus groups
Interviews
Interpersonal and Team Skills
Conflict management
Facilitation
Meeting Management
Acceptance Criteria | A set of conditions that are met before deliverables are accepted. See also deliverable and requirement.
Activity | A distinct, scheduled portion of work performed during the course of a project.
Activity Code | An alphanumeric value assigned to each activity that enables classifying, sorting, and filtering. See also activity identifier and activity label.

## Stories
4. Integration Management
[10 empty] | 9. Resource Management | 10. Communications Management | 11. Risk Management | 12. Procurement Management | 13. Stakeholder Management
Help Excel: Ctrl+F3= Manage names
|  |  |  | 1. Finding Knowledge |  |  |  | 2. Finding Mates |  |  | 1. Learn knowledge through seeking it
|  |  |  | 4. Living with Mates |  |  |  | 3. Finding Treasures |  |  | 2. Understand type of mates you need, cultivate it
|  |  |  | 5. Managing Treasures | [6 empty] | 3. Find Resources, mean to earn wealth /treasures
4. Understand how to live peacfully with mates
5. Manage all you earn - before death utilize +vely
Wealth, Children, Knowledge, People
|  |  | Love, Home, Culture |  |  |  |  | Resource,Project, Process
|  | Interest, Purpose,Religion, Skill, Language, History | [5 empty] | Finding Spouse, Friends, Mentors
Project Management Plan
Cost Management Plan
[6 empty] | = | Cost Management Plan
▪ | Units of Measure | [7 empty] | days, week, USD, Km, Kg etc
▪ | Level of Precision | [7 empty] | Degree to which cost estimates will be rounded up or down ( eg. 999.51=>1000)
▪ | Level of accuracy | [7 empty] | acceptable range ( eg.10%) used in determining realistic cost estimates is specified and may included an amount for contigencies
▪ | Organizational Procedure links | [7 empty] | The WBS provides framework for the cost management plan, allowing for consistency with the estimate, budgets, and control of costs. The WBS component used for the project cost accounting is called the control account. Each control account is assigned a unique code or account number(s) that linkes directly to the performing organization's accounting system.
▪ | Control Threshholds
▪ | Rules of Performance Measurement
▪ | Reporting Formats
▪ | Additional Details
▪
8. Quality
5. Scope
7. Cost
6. Schedule

## Index
| Knowledge Area (10) |  |  | Project Management Process Groups (5)
|  |  |  | Initiating Process Group | Planning Process Group | Executing Process Group | Monitoring and Controlling Process group | Closing Process Group
4 | Project Integration Management |  |  | 1. Develop Project Charter | 2. Develop Project Management Plan | 3. Direct and Manage Project Work 4. Manage Project Knowledge | 5. Monitor and Control Project Work 6. Perform Integrated Change Control | 7. Close Project or Phase
5 | Project Scope Management |  |  |  | 1. Plan Scope Management 2. Collect Requirements 3. Define Scope 4. Create WBS |  | 5. Validate Scope 6. Control Scope
6 | Project Schedule Management |  |  |  | 1. Plan Schedule Management 2. Define Activities 3. Sequence Activities 4. Estimate Activity Durations 5. Develop Schedule |  | 6. Control Schedule
7 | Project Cost Management |  |  |  | 1. Plan Cost Management 2. Estimate Costs 3. Determine Budget |  | 4. Control Costs
8 | Project Quality Management |  |  |  | 1. Plan Quality Management | 2. Manage Quality | 3. Control Quality
9 | Project Resource Management |  |  |  | 1. Plan Resource Management 2. Estimate Activity Resources | 3. Aquire Resources 4. Develop Team 5. Manage Team | 6. Control Resources
10 | Project Communications Management |  |  |  | 1. Plan Communications Management | 2. Manage Communications | 3. Monitor Communications
11 | Project Risk Management |  |  |  | 1. Plan Risk Management 2. Identify Risks 3. Perform Qualitative Risk Analysys 4. Peroform Quantitative Risk Analysis 5. Plan Risk Responses | 6. Implement Risk Responses | 7. Monitor Risks
12 | Project Procurement Management |  |  |  | 1. Plan Procurement Management | 2. Conduct Procurements | 3. Control Procurements
13 | Project Stakeholder Management |  |  | 1. Identify Stakeholders | 2. Plan Stakeholder Engagement | 3. Manage Stakeholder Engagement | 4. Monitor Stakeholder Engagement
|  | 1 | PMBOK Guide has 49 processes divided into 10 knowledge areas by 5 process groups
|  | 2 | 1 Knowledge areas has 5 Process groups (Integration(7))
|  | 3 | 3 knowledge areas has 3 process groups each (Scope(6), Schedule(6) & cost(4))
|  | 4 | 5 knowledge areas has 2 process groups each (Quality(3), Resource(6), Communications(3), Risk(7), Procurement(3))
|  | 5 | 1 knowledge areas has 4 process groups each (Stakeholder(4))
Note on J2: Green is for Nature. Initialing new life. Nature gives life to earth. 1. Your father and Mother (parents) - before knowing each other they were in search of their best matched partner for marriage. Either their parrents choose partner or they choose is irrelevant at this moment. Getting married is like a charter is being prepared. So taking care of pro and con is very very crucial for rest of the life. We may solve difficult problem during project execution, in the process we don't suffer - we become active in solving those problems in the process some loss may happen. But in marriage, if wrong choice is made- both and their children, all suffer. Both partners are without much planning of how to handle the whole lot of upcoming problems because when choice of partner is wrong - planning for rest of life is rare chance to happen. Incompatible partner will not be able to handle planning process. So, yes charter is when her father/ guardian and she both approve her marriage with you and appointed you as her new legal guardian, partner, husband and most importanly father of her children (Remember, she will nurse and give birth of her baby and you will be responsible for it) You got a team member with you by default to plan, execute, monitor, control and rest in PEACE with her for the rest of life. [What was the message/project: PEACE must be the final product in the family]
Note on R2: Planning time - When you get married first few weeks are honeymoon. So enjoy till you come to know very well and intimately. You will for sure land into a problem. Some mismatch. So we plan: Plan to make PEACE. You do this, this and this. I will do that, this and that. WBS, and so on. Plan is ready, but be prepared to update it as and when required. And you know who is the BOSS.
Note on Z2: Pinky - time to execute 1.When someone gets married the family responsibility to direct and manage financial stress is huge work. 2. None can teach you more than your spouse do. So, yes, manage new knowledge wisely
Note on AH2: Mid-Old age: 1. Children are now growing up - monitoring and controlling them for their benefits and your benifits. Play with them, educate them, test them. 2. In case you feel their school is not teaching them right - admit them to new school; or may be you behave with them differently to befriend them to get more better result or may be they are actually not doing well with the subjects so change the course or tutors but change something so that you can get better results
Note on AP2: Retirement or end of a generation- 1. Write a will for inheritors to distribute your properties among themselves [ Final Products is this, but for the PEACE of mind, yes it is] 2. Write a book about your life experience - life lesson for your children (project managemet plan update) 3. OPA - skills, mejor contacts, tools & techniques: children may be well educated and established in business and have their own family. Irrespective whether children are married or not they will get OPA benifits. 4. Final Report: Your current status, respect in the eyes of your children and society in general is your final report. Feedback you get is as per your achievement so far in life. Your children, your deeds and good things that you tought someone - will they benifit you after your demise?
Note on R12: 1. Wife & husband agreed to a scope management plan and how they will manage it 2. Wife needs more quality time, husband needs respect, physical needs, wife needs house-made for house work as she is getting exhausted. Husband has to do weekly twice al the bazaar work and must pay all the expenses on-time. Bathroom light must be off after use - turn on when in and turn off when you are done. 2. Wife - to maiantain house, workout to be fit to have healthy baby, husband - To do all the outside work, earn money, buy house, pay all expenses, maintain peace between wif e& mother-in-law
Note on AH12: 1. Validate Scope -. When children are growing up - both spouse will reflect on what went wrong and what went right. 2. Control Scope - Children got admited to play school, wife has to help to send children to school on time, husband will pick-up them from school. Some day wife personally has to pick-up while some day husband has to prepare them for sending them to school

## 4-Integration
| Knowledge Area | Initiating Process Group |  |  | Planning Process Group | Executing Process Group |  |  |  | Monitoring and Controlling |  | Closing Process Group
4 | Project Integration Management | 1. Develop Project Charter |  |  | 2. Develop Project Management Plan | 3. Direct and Manage Project Work 4. Manage Project Knowledge |  |  |  | 5. Monitor and Control Project Work 6. Perform Integrated Change Control |  | 7. Close Project or Phase
|  | 1 |  |  | 2 | 3 | 4 |  |  | 5 | 6 | 7
|  |  | 4 | 1. Develop Project Charter
| Inputs |  | Tools and Techniqes | [5 empty] | Outputs
1.1 | Business Documents |  | 2.1 | Expert judgment |  |  |  | 3.1 | Project Charter
1.2 | Agreements |  | 2.2 | Data Gathering |  |  |  | 3.2 | Assumption log
1.3 | Enterprise Environmental Factor |  | 2.3 | Interpersonal and Team Skills
1.4 | Organizational Process assets |  | 2.4 | Meettings
|  |  | 4 | 2. Develop Project Management Plan
| Inputs |  | Tools and Techniqes | [5 empty] | Outputs
1.1 | Project Charter |  | 2.1 | Expert judgment |  |  |  | 3.1 | Project Management Plan
1.2 | Outputs from other Processes |  | 2.2 | Data Gathering
1.3 | Enterprise Environmental Factor |  | 2.3 | Interpersonal and Team Skills
1.4 | Organizational Process assets |  | 2.4 | Meettings
|  |  | 4 | 3. Direct and Manage Project Work
| Inputs |  | Tools and Techniqes | [5 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Expert judgment |  |  |  | 3.1 | Deliverables
1.2 | Project Documents |  | 2.2 | Project Management Information Systems |  |  |  | 3.2 | Work Performance Data
1.3 | Approved Changed Requests |  | 2.3 | Mettings |  |  |  | 3.3 | Issue Log
1.4 | Enterprise Environmental Factors | [6 empty] | 3.4 | Change Requests
| Organizational Process assets | [6 empty] | 3.5 | Project Management Plan updates
[8 empty] | 3.6 | Project documents updates
[8 empty] | 3.7 | Organizational process assess updates
|  |  | 4 | 4. Manage Project Knowledge
| Inputs |  | Tools and Techniqes | [5 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Expert judgment |  |  |  | 3.1 | Lesson Learned Register
1.2 | Project Documents |  | 2.2 | Knowledge Management |  |  |  | 3.2 | Project Management Plan updates
1.3 | Deliverables |  | 2.3 | Information management |  |  |  | 3.3 | Organizational process assess updates
1.4 | Enterprise Environmental Factor |  | 2.4 | Interpersonal and Team Skills
1.5 | Organizational Process assets
|  |  | 4 | 5. Monitor and Control Project Work
Inputs |  |  | Tools and Techniqes | [5 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Expert judgment |  |  |  | 3.1 | Work Performance Reports
1.2 | Project Documents |  | 2.2 | Data Analysis |  |  |  | 3.2 | Change Requests
1.3 | Work Performance Information |  | 2.3 | Decision Making |  |  |  | 3.3 | Project Management Plan updates
1.4 | Agreements |  | 2.4 | Meetings |  |  |  | 3.4 | Project documents updates
1.5 | Enterprise Environmental Factor
1.6 | Organizational Process assets
|  |  | 4 | 6. Perform Integrated Change Control
Inputs |  |  | Tools and Techniqes | [5 empty] | Outputs
1.1 | Project Charter |  | 2.1 | Expert judgment |  |  |  | 3.1 | Approved Change Requests
1.2 | Project Management Plan |  | 2.2 | Change Control Tools |  |  |  | 3.2 | Project Management Plan updates
1.3 | Project Management Plan updates |  | 2.3 | Data analysis |  |  |  | 3.3 | Organizational process assets updates
1.4 | Final product, service, or result transition |  | 2.4 | Decision making |  |  |  | 3.4
1.5 | Business Documents |  | 2.5 | Meeting
1.6 | Agreements
|  |  | 4 | 7. Close Project or Phase
Inputs |  |  | Tools and Techniqes | [5 empty] | Outputs
1.1 | Project Charter |  | 2.1 | Expert judgment |  |  |  | 3.1 | Project Management Plan updates
1.2 | Project Management Plan |  | 2.2 | Data analysis |  |  |  | 3.2 | Final product, service, or result transition
1.3 | Project Documents |  | 2.3 | Meeting |  |  |  | 3.3 | Final report
1.4 | Accepted Deliverables | [6 empty] | 3.4 | Organizational process assets updates
1.5 | Business Documents
1.6 | Agreements
1.7 | Procurement Documentation
1.8 | Organizational Process assets
Note on B13: >Business Case
Note on B15: >Contracts >Memorandums of understanding (MOU) >Service Level Agreement (SLA) >Letter of intent >Verbal agreements >email >other writen agreements

## 5-Scope
| Knowledge Area | Initiating Process Group |  |  | Planning Process Group |  |  |  | Executing Process Group |  |  | Monitoring and Controlling |  | Closing Process Group
5 | Project Scope Management |  |  |  | 1. Plan Scope Management 2. Collect Requirements 3. Define Scope 4. Create WBS | [6 empty] | 5. Validate Scope 6. Control Scope
[5 empty] | 1 | 2 | 3 | 4 |  |  |  | 5 | 6
|  |  | 5 | 1. Plan Scope Management
| Inputs |  | Tools and Techniqes | [7 empty] | Outputs
1.1 | Project Charter |  | 2.1 | Expert judgment | [5 empty] | 3.1 | Scope management plan
1.2 | Project Management Plan |  | 2.2 | Data analysis | [5 empty] | 3.2 | Requirements management plan
1.3 | Enterprise Environmental Factors |  | 2.3 | Meettings
1.4 | Organizational Process assets |  | 2.4
|  |  | 5 | 2. Collect Requirements
| Inputs |  | Tools and Techniqes | [7 empty] | Outputs
1.1 | Project Charter |  | 2.1 | Expert judgment | [5 empty] | 3.1 | Requirements documentations
1.2 | Project Management Plan |  | 2.2 | Data gathering | [5 empty] | 3.2 | Requirements traceability matrix
1.3 | Project documents |  | 2.3 | Data analysis
1.4 | Business documents |  | 2.4 | Decision making
1.5 | Agreements |  | 2.5 | Data representation
1.6 | Enterprise Environmental Factors |  | 2.6 | Interpersonal and team skills
1.7 | Organizational Process assets |  | 2.7 | Context diagram
|  |  | 2.8 | Prototypes
|  |  | 5 | 3. Define Scope
| Inputs |  | Tools and Techniqes | [7 empty] | Outputs
1.1 | Project Charter |  | 2.1 | Expert judgment | [5 empty] | 3.1 | Project scope statement
1.2 | Project Management Plan |  | 2.2 | Data analysis | [5 empty] | 3.2 | Project documents updates
1.3 | Project documents |  | 2.3 | Decision making
1.4 | Enterprise Environmental Factors |  | 2.4 | Interpersonal and team skills
1.5 | Organizational Process assets |  | 2.5 | Product analysis
|  |  | 5 | 4. Create WBS
| Inputs |  | Tools and Techniqes | [7 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Expert judgment | [5 empty] | 3.1 | Scope baseline
1.2 | Project Documents |  | 2.2 | Decomposition | [5 empty] | 3.2 | Project documents updates
1.3 | Enterprise Environmental Factor |  | 2.3
1.4 | Organizational Process assets |  | 2.4
|  |  | 5 | 5. Validate Scope
Inputs |  |  | Tools and Techniqes | [7 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Inspection | [5 empty] | 3.1 | Accepted Deliverables
1.2 | Project Documents |  | 2.2 | Decision Making | [5 empty] | 3.2 | Work performance information
1.3 | Verified Deliverables | [8 empty] | 3.3 | Change request
1.4 | Work performance data | [8 empty] | 3.4 | Project documents updates
|  |  | 5 | 6. Control Scope
Inputs |  |  | Tools and Techniqes | [7 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Data analysis | [5 empty] | 3.1 | Work performance information
1.2 | Project Documents | [8 empty] | 3.2 | Change request
1.3 | Work performance data | [8 empty] | 3.3 | Project Management Plan updates
1.4 | Organizational Process assets | [8 empty] | 3.4 | Project documents updates
Note on B13: You are married spouse that's the first condition
Note on O13: You elders ( including your parents, grand-prents, and prents-in-laws, specialist, marriage-councillor) --> Judgement provided based upon expertise in an application area, knowledge area, discipline, industry, etc., an appropriate for the activity performed.
Note on AF13: This is the document you get from this process. It's component of Project Management Plan
Note on B15: a. Quality Management Plan ( Do we need Car, New Flat? Quality of Life) b. Project Life Cycle Description (Do you want to go for higher study, Have children -how many, move to new city?) c. Development Aproach ( Or we can decide something for later - agile?) Here you are creating a new plan for scope management and Requirement management plan
Note on O15: -Alternative analysis Organize, Assess and evaluate data and information
Note on AF15: It's a component of Project Management Plan. - How requirements activities will be planned, tracked, and reported. -Configuration Management activities: how changes will be initiated, how impact will be analyzed & tracked, and reported; as well as the authorization levels required to approve these changes; - Requirement prioritization process - traceability matrix
Note on B17: Social, cultural, religious, home upbringing as well various govermanet policy factors
Note on O17: You need to seat together and find out more requirements, either together or with the elders
Note on B19: Your experience from elders, neigbours, in-laws, novel, news and so on.
Note on O99: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Voting

## 6-Schedule
| Knowledge Area | Initiating Process Group |  |  | Planning Process Group |  |  |  |  | Executing Process Group |  |  | Monitoring and Controlling | Closing Process Group
6 | Project Scope Management |  |  |  | 1. Plan schedule management 2. Define activities 3. Sequence activities 4. Estimate activity durations 5. Develop schedule | [7 empty] | 6. Control schedule
[5 empty] | 1 | 2 | 3 | 4 | 5 |  |  |  | 6
|  |  | 6 | 1. Plan Schedule Management
| Inputs |  | Tools and Techniqes | [8 empty] | Outputs
1.1 | Project Charter |  | 2.1 | Expert judgement | [6 empty] | 3.1 | Schedule Management Plan
1.2 | Project Management Plan |  | 2.2 | Data analysis
1.3 | Enterprise Environmental Factor |  | 2.3 | Meettings
1.4 | Organizational Process assets
|  |  | 6 | 2. Define activities
| Inputs |  | Tools and Techniqes | [8 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Expert judgement | [6 empty] | 3.1 | Activity list
1.2 | Enterprise Environmental Factor |  | 2.2 | Decomposition | [6 empty] | 3.2 | Activity Atributes
1.3 | Organizational Process assets |  | 2.3 | Rolling wave planning | [6 empty] | 3.3 | Milestone list
|  |  | 2.4 | Meeting | [6 empty] | 3.4 | Change request
[11 empty] | 3.5 | Project management plan updates
|  |  | 6 | 3. Sequence activities
| Inputs |  | Tools and Techniqes | [8 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Precedence diagraming method | [6 empty] | 3.1 | Project schedule network diagram
1.2 | Project Documents |  | 2.2 | Dependency determination and integration | [6 empty] | 3.2 | Project documents updates
1.3 | Enterprise Environmental Factors |  | 2.3 | Leads and Lags
1.4 | Organizational Process assets |  | 2.4 | Project management information systems
|  |  | 6 | 4. Estimate activity durations
| Inputs |  | Tools and Techniqes | [8 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Expert judgement | [6 empty] | 3.1 | Lesson Learned Register
1.2 | Project Documents |  | 2.2 | Analogous estimation | [6 empty] | 3.2 | Project Management Plan updates
1.3 | Enterprise Environmental Factor |  | 2.3 | Parametric estimation | [6 empty] | 3.3 | Organizational process assess updates
1.4 | Organizational Process assets |  | 2.4 | Three-point estimation
|  |  | 2.5 | Bottom-up estimation
|  |  | 2.6 | Data analysis
|  |  | 2.7 | Decision making
|  |  | 2.8 | Meeting
|  |  | 6 | 5. Develop schedule
Inputs |  |  | Tools and Techniqes | [8 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Schedule network analysis | [6 empty] | 3.1 | Schedule baseline
1.2 | Project Documents |  | 2.2 | Critical path method | [6 empty] | 3.2 | Project schedule
1.3 | Agreements |  | 2.3 | Resource optimization | [6 empty] | 3.3 | Schedule data
1.4 | Enterprise Environmental Factor |  | 2.4 | Data analysis | [6 empty] | 3.4 | Project Calenders
1.5 | Organizational Process assets |  | 2.5 | Leads and lags | [7 empty] | Change requests
|  |  | 2.6 | Schedule compression | [7 empty] | Project management plan updates
|  |  | 2.7 | Project management information system | [7 empty] | Project documents updates
|  |  | 2.8 | Agile release planning
|  |  | 6 | 6. Control schedule
Inputs |  |  | Tools and Techniqes | [8 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Data analysis | [6 empty] | 3.1 | Work performance information
1.2 | Project Documents |  | 2.2 | Critical path method | [6 empty] | 3.2 | Schedule forecasts
1.3 | Work performance data |  | 2.3 | Project management information system | [6 empty] | 3.3 | Change requests
1.4 | Organizational Process assets |  | 2.4 | Resource optimaization | [6 empty] | 3.4 | Project management plan updates
|  |  | 2.5 | Leads and lags | [7 empty] | Project documents updates
Schedule compression

## 6-Cost
| Knowledge Area | Initiating Process Group |  |  | Planning Process Group |  |  | Executing Process Group |  |  | Monitoring and Controlling | Closing Process Group
7 | Project Integration Management |  |  |  | 1. Plan Cost Management 2. Estimate Costs 3. Determine Budget | [5 empty] | 4. Control Costs
[5 empty] | 1 | 2 | 3 |  |  |  | 4
|  |  | 7 | 1. Plan Cost Management
| Inputs |  | Tools and Techniqes | [6 empty] | Outputs
1.1 | Project Charter |  | 2.1 | Expert judgment |  |  |  |  | 3.1 | Cost Management Plan |  |  | =
1.2 | Project Management Plan |  | 2.2 | Data analysis
1.3 | Enterprise Environmental Factor |  | 2.3 | Meettings
1.4 | Organizational Process assets
|  |  | 7 | 2. Estimate Costs
| Inputs |  | Tools and Techniqes | [6 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Expert judgment |  |  |  |  | 3.1 | Cost Estimates
1.2 | Project Documents |  | 2.2 | Analogous estimating |  |  |  |  | 3.2 | Basis of estimates
1.3 | Enterprise Environmental Factor |  | 2.3 | Parametric estimating |  |  |  |  | 3.3 | Project Documents updates
1.4 | Organizational Process assets |  | 2.4 | Bottom-up estimating
|  |  | 2.5 | Three-point estimating
|  |  | 2.6 | Data analysis
|  |  | 2.7 | Project Management Information System
|  |  | 2.8 | Decision Making
|  |  | 7 | 3. Determine Budget
| Inputs |  | Tools and Techniqes | [6 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Expert judgment |  |  |  |  | 3.1 | Cost baseline
1.2 | Project Documents |  | 2.2 | Cost Agregation |  |  |  |  | 3.2 | Project funding requirements
1.3 | Business Documents |  | 2.3 | Data analysis |  |  |  |  | 3.3 | Project documents updates
1.4 | Agreements |  | 2.4 | Historical information review
1.5 | Enterprise Environmental Factor |  | 2.5 | Funding limit reconsiliation
1.6 | Organizational Process assets |  | 2.6 | Financing
|  |  | 7 | 4. Control Costs
| Inputs |  | Tools and Techniqes | [6 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Expert judgment |  |  |  |  | 3.1 | Work performance information
1.2 | Project Documents |  | 2.2 | Data analysis |  |  |  |  | 3.2 | Cost forecasts
1.3 | Project funding requirements |  | 2.3 | To-complete performance index |  |  |  |  | 3.3 | Change requests
1.4 | Work performance data |  | 2.4 | Project management information system | [5 empty] | Project Management plan updates
1.5 | Organizational Process assets
Note on B15: >Schedule Management Plan >Risk Management Plan
Note on O26: It determines the monetary resources required for the project. This process is performed periodically throughout the project as needed.
Note on B30: -Cost Management Plan -Quality Management Plan -Scope Baseline
Note on AF30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Initial phase -> Rough Order of magnitude ( estimate range -25% to 75%) Definitive Estimate ( Estimate range -5% to +10%)
Note on B32: -Lession learned register - Project Schedule - Resource Requirements - Risk Register
Note on AF34: - Assumption Log - Leassion Learned - Risk Register
Note on O38: Cost based on -> Most Likely (cM) is realistic Optimistic (c0) is best-case Pessimistic (cP) is worst-case Expected Cost (cE) 1) Triangular distribution cE=(c0+cM+cP)/3 2)Beta distribution cE=(c0+4cM+cP)/6
Note on O40: - Alternative Analaysis - Reserve Analysis - Cost of Quality
Note on O44: - Voting
CV
CV=𝐸𝑉−𝐴𝐶
CPI
CPI=𝐸𝑉/𝐴𝐶

## 8-Quality
| Knowledge Area | Initiating Process Group |  |  | Planning Process Group |  |  | Executing Process Group |  |  | Monitoring and Controlling |  |  | Closing Process Group
8 | Project Integration Management |  |  |  | 1. Plan Quality Management |  |  | 2. Manage Quality |  |  | 3. Control Quality
[5 empty] | 1 |  |  | 2 |  |  | 3
|  |  | 4 | 1. Plan Quality Management
| Inputs |  | Tools and Techniqes | [6 empty] | Outputs
1.1 | Project Charter |  | 2.1 | Expert judgment |  |  |  |  | 3.1 | Quality Management Plan
1.2 | Project Management Plan |  | 2.2 | Data Gathering |  |  |  |  | 3.2 | Quality Metrics
1.3 | Project Documents |  | 2.3 | Data Analysis |  |  |  |  | 3.3 | Project Management Plan updates
1.4 | Enterprise Environmental Factors |  | 2.4 | Decision Making |  |  |  |  | 3.4 | Project documents updates
1.5 | Organizational Process assets |  | 2.5 | Data representation
|  |  | 2.6 | Test and inspection planning
|  |  | 2.7 | Meeting
|  |  | 4 | 2. Manage Quality
| Inputs |  | Tools and Techniqes | [6 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Data Gathering |  |  |  |  | 3.1 | Quality reports
1.2 | Project Documents |  | 2.2 | Data Analysis |  |  |  |  | 3.2 | Test and evaluation documents
1.3 | Organizational Process assets |  | 2.3 | Decision Making |  |  |  |  | 3.3 | Change requests
|  |  | 2.4 | Data representation |  |  |  |  | 3.4 | Project Management Plan updates
|  |  | 2.5 | Audits |  |  |  |  | 3.5 | Project documents updates
|  |  | 2.6 | Design for X
|  |  | 2.7 | Problem Solving
|  |  | 2.8 | Quality improvement methods
|  |  | 4 | 3. Control Quality
| Inputs |  | Tools and Techniqes | [6 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Data Gathering |  |  |  |  | 3.1 | Quality Control Measurements
1.2 | Project Documents |  | 2.2 | Data Analysis |  |  |  |  | 3.2 | Verified deliverables
1.3 | Approved Changed Requests |  | 2.3 | Inspection |  |  |  |  | 3.3 | Work performance information
1.4 | Deliverables |  | 2.4 | Testing/Product evaluations |  |  |  |  | 3.4 | Change requests
1.5 | Work performance data |  | 2.5 | Data representation |  |  |  |  | 3.5 | Project Management Plan updates
1.6 | Enterprise Environmental Factors |  | 2.6 | Meetings |  |  |  |  | 3.6 | Project documents updates
1.7 | Organizational Process assets
Quality templates from OPA
Plan Quality Management
Quality Management plan
To other processes
[10 empty] | Manage Quality |  |  |  |  | Quality reports
Quality metrics
Quality Control measurements
[12 empty] | Test and evaluation documents |  |  |  | Work performance information
Quality reports
|  |  | Project Integration Management | [9 empty] | Control Quality
Deliverables
[8 empty] | Work performance data | [8 empty] | Validate scope
Verified deliverables
|  |  | 4 | 4. Manage Project Knowledge
| Inputs |  | Tools and Techniqes | [6 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Data Gathering |  |  |  |  | 3.1 | Lesson Learned Register
1.2 | Project Documents |  | 2.2 | Knowledge Management |  |  |  |  | 3.2 | Project Management Plan updates
1.3 | Quality Control Measurements |  | 2.3 | Information management |  |  |  |  | 3.3 | Organizational process assess updates
1.4 | Enterprise Environmental Factor |  | 2.4 | Decision Making
1.5 | Organizational Process assets
|  |  | 4 | 5. Monitor and Control Project Work
Inputs |  |  | Tools and Techniqes | [6 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Data Gathering |  |  |  |  | 3.1 | Work Performance Reports
1.2 | Project Documents |  | 2.2 | Data Analysis |  |  |  |  | 3.2 | Change Requests
1.3 | Work Performance Information |  | 2.3 | Decision Making |  |  |  |  | 3.3 | Project Management Plan updates
1.4 | Agreements |  | 2.4 | Meetings |  |  |  |  | 3.4 | Project documents updates
1.5 | Enterprise Environmental Factor
1.6 | Organizational Process assets
|  |  | 4 | 6. Perform Integrated Change Control
Inputs |  |  | Tools and Techniqes | [6 empty] | Outputs
1.1 | Project Charter |  | 2.1 | Expert judgment |  |  |  |  | 3.1 | Approved Change Requests
1.2 | Project Management Plan |  | 2.2 | Change Control Tools |  |  |  |  | 3.2 | Project Management Plan updates
1.3 | Project Management Plan updates |  | 2.3 | Data analysis |  |  |  |  | 3.3 | Organizational process assets updates
1.4 | Final product, service, or result transition |  | 2.4 | Decision making |  |  |  |  | 3.4
1.5 | Business Documents |  | 2.5 | Meeting
1.6 | Agreements
|  |  | 4 | 7. Close Project or Phase
Inputs |  |  | Tools and Techniqes | [6 empty] | Outputs
1.1 | Project Charter |  | 2.1 | Expert judgment |  |  |  |  | 3.1 | Project Management Plan updates
1.2 | Project Management Plan |  | 2.2 | Data analysis |  |  |  |  | 3.2 | Final product, service, or result transition
1.3 | Project Documents |  | 2.3 | Meeting |  |  |  |  | 3.3 | Final report
1.4 | Accepted Deliverables | [7 empty] | 3.4 | Organizational process assets updates
1.5 | Business Documents
1.6 | Agreements
1.7 | Procurement Documentation
1.8 | Organizational Process assets
Note on B15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: >Requirements Management Plans >Risk Management Plan >Stakeholder Engagement Plan >Scope Baseline
Note on O15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: >Benchmarking >Brainstorming >Interviews
Note on B17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: >Asumption log >Requirements Documentation >Requirement Traceability Matrix >Risk Register >Stakeholder Register
Note on O17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: >Cost-Benifit analysis >Cost of quality
Note on AF17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: >Risk Management Plan >Scope Baseline
Note on O19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: >Multicriterioa decision analysis
Note on AF19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: >Lessons Learned Register >Requirements Traceability Matrix >Risk Register >Stakeholder Register
Note on O21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: >Flowcharts >Logical Data Model >Matrix Diagram >Mind Mapping

## 9-Resource
| Knowledge Area | Initiating Process Group |  |  | Planning Process Group |  | Executing Process Group |  |  |  |  | Monitoring and Controlling | Closing Process Group
9 | Project Resource Management |  |  |  | 1. Plan Resource Management 2. Estimate Activity Resources |  | 3. Aquire Resources 4. Develop Team 5. Manage Team |  |  |  |  | 6. Control Resources
[5 empty] | 1 | 2 | 3 | 4 | 5 |  |  | 6
|  |  | 9 | 1. Plan Resource Management Process
Inputs |  |  | Tools and Techniqes | [7 empty] | Outputs
1.1 | Project Charter |  | 2.1 | Expert judgment | [5 empty] | 3.1 | Resource Management Plan
1.2 | Project Management Plan |  | 2.2 | Data Representation | [5 empty] | 3.2 | Team Charter
1.3 | Project Documents |  | 2.3 | Organizational Theory | [5 empty] | 3.3 | Project documents updates
1.4 | Enterprise Environmental Factor |  | 2.4 | Mettings
1.5 | Organizational Process assets
|  |  | 9 | 2.Estimate Activity Resources
Inputs |  |  | Tools and Techniqes | [7 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Expert Judgment | [5 empty] | 3.1 | Resource Requirements
1.2 | Project Documents |  | 2.2 | Bottom-up Estimating | [5 empty] | 3.2 | Basis Of Estimates
1.3 | Enterprise Environmental Factor |  | 2.3 | Analogous Estimating | [5 empty] | 3.3 | Resource Breakdown Structure
1.4 | Organizational Process assets |  | 2.4 | Parametric Estimating | [5 empty] | 3.4 | Project Documents Updates
|  |  | 2.5 | Data Analysis
|  |  | 2.6 | Project Management Information System
|  |  | 2.7 | Meetings
|  |  | 9 | 3. Aquire Resources
Inputs |  |  | Tools and Techniqes | [7 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Decision Making | [5 empty] | 3.1 | Physical Resource assignments
1.2 | Project Documents |  | 2.2 | Interpersonal and Team Skills | [5 empty] | 3.2 | Project Team Assignments
1.3 | Enterprise Environmental Factor |  | 2.3 | Pre-assignment | [5 empty] | 3.3 | Resource Calenders
1.4 | Organizational Process assets |  | 2.4 | Virtual Teams | [5 empty] | 3.4 | Change Request
[10 empty] | 3.5 | Project Management Plan updates
[10 empty] | 3.6 | Project Documents Updates
[10 empty] | 3.7 | Enterprise Environmental Factors Updates
[10 empty] | 3.8 | Organizational Process Assests Updates
|  |  | 9 | 4. Develop Team
Inputs |  |  | Tools and Techniqes | [7 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Colocation | [5 empty] | 3.1 | Team Performance Assessments
1.2 | Project Documents |  | 2.2 | Virtual Teams | [5 empty] | 3.2 | Change Requests
1.3 | Enterprise Environmental Factor |  | 2.3 | Communication technology | [5 empty] | 3.3 | Project Management Plan Updates
1.4 | Organizational Process assets |  | 2.4 | Interpersonal and Team Skills | [5 empty] | 3.4 | Project Documents Updates
|  |  | 2.5 | Recognition and Rewards | [5 empty] | 3.5 | Enterprise Environmental factors Updates
|  |  | 2.6 | Training | [5 empty] | 3.6 | Organizational Process Assests Updates
|  |  | 2.7 | Individual and Team assignments
|  |  | 2.8 | Meeting
|  |  | 9 | 5. Manage Team
Inputs |  |  | Tools and Techniqes | [7 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Interpersonal and Team Skills | [5 empty] | 3.1 | Change Requests
1.2 | Project Documents |  | 2.2 | Project Management Information System | [5 empty] | 3.2 | Project Management Plan Updates
1.3 | Work Performance Reports |  | 2.3 | [6 empty] | 3.3 | Project Documents Updates
1.4 | Team Performance assessments |  | 2.4 | [6 empty] | 3.4 | Enterprise Environmental factors Updates
1.5 | Enterprise Environmental Factor
1.6 | Organizational Process assets
|  |  | 9 | 6. Control Resources
Inputs |  |  | Tools and Techniqes | [7 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Data Analysis | [5 empty] | 3.1 | Work Performance Information
1.2 | Project Documents |  | 2.2 | Problem Solving | [5 empty] | 3.2 | Change Request
1.3 | Work Performance Data |  | 2.3 | Interpersonal and Team Skills | [5 empty] | 3.3 | Project Management Plan Updates
1.4 | Enterprise Environmental Factor |  | 2.4 | Project Management Information System | [6 empty] | Project Documents Updates
Organizational Process assets

## 10-Communications
| Knowledge Area | Initiating Process Group |  |  | Planning Process Group | Executing Process Group |  |  | Monitoring and Controlling | Closing Process Group
10 | Project Integration Management |  |  |  | 1. Plan Communication Management | 2. Manage Communications |  |  | 3. Monitor Communications
[5 empty] | 1 | 2 |  |  | 3
|  |  | 10 | 1. Plan Communication Management
| Inputs |  | Tools and Techniqes |  |  |  |  | Outputs
1.1 | Business Documents |  | 2.1 | Expert Judgment |  |  | 3.1 | Project Charter
1.2 | Agreements |  | 2.2 | Data Gathering |  |  | 3.2 | Assumption log
1.3 | Enterprise Environmental Factor |  | 2.3 | Interpersonal and Team Skills
1.4 | Organizational Process assets |  | 2.4 | Meettings
|  |  | 10 | 2. Manage Communications
| Inputs |  | Tools and Techniqes |  |  |  |  | Outputs
1.1 | Project Charter |  | 2.1 | Expert Judgment |  |  | 3.1 | Project Management Plan
1.2 | Outputs from other Processes |  | 2.2 | Data Gathering
1.3 | Enterprise Environmental Factor |  | 2.3 | Interpersonal and Team Skills
1.4 | Organizational Process assets |  | 2.4 | Meettings
|  |  | 10 | 3. Monitor Communications
| Inputs |  | Tools and Techniqes |  |  |  |  | Outputs
1.1 | Project Management Plan |  | 2.1 | Expert judgment |  |  | 3.1 | Deliverables
1.2 | Project Documents |  | 2.2 | Project Management Information Systems |  |  | 3.2 | Work Performance Data
1.3 | Approved Changed Requests |  | 2.3 | Mettings |  |  | 3.3 | Issue Log
1.4 | Enterprise Environmental Factors | [5 empty] | 3.4 | Change Requests
| Organizational Process assets | [5 empty] | 3.5 | Project Management Plan updates
[7 empty] | 3.6 | Project documents updates
[7 empty] | 3.7 | Organizational process assess updates
Note on B13: >Business Case
Note on B15: >Contracts >Memorandums of understanding (MOU) >Service Level Agreement (SLA) >Letter of intent >Verbal agreements >email >other writen agreements

## 11-Risk
| Knowledge Area | Initiating Process Group |  |  | Planning Process Group |  |  |  |  | Executing Process Group |  |  | Monitoring and Controlling | Closing Process Group
11 | Project Integration Management |  |  |  | 1. Plan Risk Management 2. Identify Risk 3. Perform Qualitative Risk Analysis 4. Perform Quantitative Risk Analysis 5. Plan Risk Responses |  |  |  |  | 6. Inspect Risk Responses |  |  | 7. Monitor Risk
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  |  | 7
|  |  | 11 | 1. Plan Risk Management
| Inputs |  | Tools and Techniqes | [8 empty] | Outputs
1.1 | Project Charter |  | 2.1 | Expert Judgment | [6 empty] | 3.1 | Risk Management Plan
1.2 | Project Management Plan |  | 2.2 | Data Analysis
1.3 | Project Documents |  | 2.3 | Meettings
1.4 | Enterprise Environmental Factors
1.5 | Organizational Process assets
|  |  | 11 | 2. Identify Risk
| Inputs |  | Tools and Techniqes | [8 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Expert Judgment | [6 empty] | 3.1 | Risk Register
1.2 | Project Documents |  | 2.2 | Data Gathering | [6 empty] | 3.2 | Risk Report
1.3 | Agreements |  | 2.3 | Data analysis | [6 empty] | 3.3 | Project documents updates
1.4 | Procurement documentations |  | 2.4 | Interpersonal and team Skills
1.5 | Enterprise Environmental Factors |  | 2.5 | Prompt lists
1.6 | Organizational Process assets |  | 2.6 | Meetings
|  |  | 11 | 3. Perform Qualitative Risk Analysis
| Inputs |  | Tools and Techniqes | [8 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Expert Judgment | [6 empty] | 3.1 | Project documents updates
1.2 | Project Documents |  | 2.2 | Data Gathering | [6 empty] | 3.2
1.3 | Enterprise Environmental Factors |  | 2.3 | Data analysis | [6 empty] | 3.3
1.4 | Organizational Process assets |  |  | Interpersonal and team Skills | [6 empty] | 3.4
|  |  |  | Risk Catagorization | [6 empty] | 3.5
|  |  |  | Data Representation | [6 empty] | 3.6
|  |  |  | Meetings | [6 empty] | 3.7
|  |  | 11 | 4. Perform Quantitative Risk Analysis
| Inputs |  | Tools and Techniqes | [8 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Expert Judgment | [6 empty] | 3.1 | Project documents updates
1.2 | Project Documents |  | 2.2 | Data Gathering | [6 empty] | 3.2
1.3 | Enterprise Environmental Factors |  | 2.3 | Interpersonal and team Skills | [6 empty] | 3.3
1.4 | Organizational Process assets |  | 2.4 | Representations of uncertainty
Data Analysis
|  |  | 11 | 5. Plan Risk Responses
Inputs |  |  | Tools and Techniqes | [8 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Expert Judgment | [6 empty] | 3.1 | Change Requests
1.2 | Project Documents |  | 2.2 | Data Gathering | [6 empty] | 3.2 | Project Management Plan updates
1.3 | Enterprise Environmental Factors |  | 2.3 | Interpersonal and team Skills | [6 empty] | 3.3 | Project documents updates
1.4 | Organizational Process assets |  | 2.4 | Strategies for Threats
|  |  | 2.5 | Strategies for opportunities
|  |  | 2.6 | Contingent response strategies
|  |  | 2.7 | Strategies for overall project risk
|  |  | 2.8 | Data analysis
|  |  | 2.9 | Decision making
|  |  | 11 | 6. Inspect Risk Responses
Inputs |  |  | Tools and Techniqes | [8 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Expert judgment | [6 empty] | 3.1 | Change Requests
1.2 | Project Documents |  | 2.2 | Interpersonal and team Skills | [6 empty] | 3.2 | Project documents updates
1.3 | Organizational Process assets |  | 2.3 | Project Management Information System
|  |  | 11 | 7. Monitor Risk
Inputs |  |  | Tools and Techniqes | [8 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Data analysis | [6 empty] | 3.1 | Work Performance Information
1.2 | Project Documents |  | 2.2 | Audits | [6 empty] | 3.2 | Change Requests
1.3 | Work Performance data |  | 2.3 | Meetings | [6 empty] | 3.3 | Project Management Plan updates
1.4 | Work Performance reports | [9 empty] | 3.4 | Project documents updates
[11 empty] | 3.5 | Organizational Process updates

## 12-Procurement
| Knowledge Area | Initiating Process Group |  |  | Planning Process Group | Executing Process Group |  |  | Monitoring and Controlling | Closing Process Group
12 | Project Procurement Management |  |  |  | 1. Procurement Management Plan | 2. Conduct Procurements |  |  | 3. Control Procurements |  | Questions
[5 empty] | 1 | 2 |  |  | 3
|  |  | 12 | 1. Procurement Management Plan
| Inputs |  | Tools and Techniqes |  |  |  |  | Outputs
1.1 | Project Charter |  | 2.1 | Expert Judgment |  |  | 3.1 | Procurement Management Plan
1.2 | Business Documents |  | 2.2 | Data Gathering |  |  | 3.2 | Procurement Strategy
1.3 | Project Management Plan |  | 2.3 | Data Analysis |  |  | 3.3 | Bid Documents
1.4 | Project Documents |  | 2.4 | Source Selection analysis |  |  | 3.4 | Procurement Statement of Work
1.5 | Enterprise Environmental Factor |  | 2.5 | Meettings |  |  | 3.5 | Source Selection Criteria
1.6 | Organizational Process assets | [5 empty] | 3.6 | Make-or-buy decisions
[7 empty] | 3.7 | Indipendent cost estimates
[7 empty] | 3.8 | Change Requests
[7 empty] | 3.9 | Project Documents Updates
[7 empty] | 3.10 | Organizational Process Assets Updates
|  |  | 12 | 2. Conduct Procurements
| Inputs |  | Tools and Techniqes |  |  |  |  | Outputs
1.1 | Project Management Plan |  | 2.1 | Expert Judgment |  |  | 3.1 | Selected Sellers
1.2 | Project Documents |  | 2.2 | Advertising |  |  | 3.2 | Agreements
1.3 | Procurement Documentation |  | 2.3 | Bidder Conferences |  |  | 3.3 | Change Requests
1.4 | Seller Proposals |  | 2.4 | Data Analysis |  |  | 3.4 | Project Management Plan updates
1.5 | Enterprise Environmental Factors |  | 2.5 | Interpersonal and team skills |  |  | 3.5 | Project documents updates
1.6 | Organizational Process assets | [5 empty] | 3.6 | Organizational process assess updates
|  |  | 12 | 3. Control Procurements
| Inputs |  | Tools and Techniqes |  |  |  |  | Outputs
1.1 | Project Management Plan |  | 2.1 | Expert Judgment |  |  | 3.1 | Closed Procuremnets
1.2 | Project Documents |  | 2.2 | Claim Administration |  |  | 3.2 | Work performance Information
1.3 | Agreements |  | 2.3 | Data Analysis |  |  | 3.3 | Change Requests
1.4 | Procurement documentation |  | 2.4 | Inspection |  |  | 3.4 | Procurement documentation Updates
1.5 | Approved change requests |  | 2.5 | Audits |  |  | 3.5 | Project Management Plan updates
1.6 | Work performance data | [5 empty] | 3.6 | Project documents updates
1.7 | Enterprise Environmental Factors | [5 empty] | 3.7 | Organizational process assess updates
1.8 | Organizational Process assets

## 13-Stakeholder
13 | Project Integration Management | 1. Identify Stakeholders |  |  | 2. Plan Stakeholder Engagement | 3. Manage Stakeholder Engagement |  |  |  | 4. Monitor Stakeholder Engagement | Questions
|  | 1 |  |  | 2 | 3 |  |  |  | 4
|  |  | 13 | 1. Identify Stakeholders
| Inputs |  | Tools and Techniqes | [5 empty] | Outputs
1.1 | Project Charter |  | 2.1 | Expert judgment |  |  |  | 3.1 | Stakeholder register
1.2 | Business documents |  | 2.2 | Data Gathering |  |  |  | 3.2 | Change requests
1.3 | Project management plan |  | 2.3 | Data Analysis |  |  |  | 3.3 | Project management plan update
1.4 | Project documents |  | 2.4 | Data representation |  |  |  | 3.4 | Project documents update
1.5 | Agreements |  | 2.5 | Meetings
1.6 | Enterprise environmental factors
1.7 | Organizational process assets
cam
|  |  | 13 | 2. Plan Stakeholder Engagement
| Inputs |  | Tools and Techniqes | [5 empty] | Outputs
1.1 | Project Charter |  | 2.1 | Expert judgment |  |  |  | 3.1 | Stakeholder engagement plan
1.2 | Project management plan |  | 2.2 | Data Gathering
1.3 | Project documents |  | 2.3 | Data Analysis
1.4 | Agreements |  | 2.4 | Decision making
1.5 | Enterprise environmental factors |  | 2.5 | Data representation
1.6 | Organizational process assets |  | 2.6 | Meetings
|  |  | 13 | 3. Manage Stakeholder Engagement
| Inputs |  | Tools and Techniqes | [5 empty] | Outputs
1.1 | Project management plan |  | 2.1 | Expert judgment |  |  |  | 3.1 | Change Requests
1.2 | Project documents |  | 2.2 | Communication Skills |  |  |  | 3.2 | Project Management Plan updates
1.3 | Enterprise Environmental Factors |  | 2.3 | Interpersonal and team skills |  |  |  | 3.3 | Project documents updates
1.4 | Organizational Process assets |  | 2.4 | Ground rules
|  |  | 2.5 | Meetings
|  |  | 13 | 4. Monitor Stakeholder Engagement
| Inputs |  | Tools and Techniqes | [5 empty] | Outputs
1.1 | Project Management Plan |  | 2.1 | Data Analysis |  |  |  | 3.1 | Work performance information
1.2 | Project Documents |  | 2.2 | Decision making |  |  |  | 3.2 | Change requests
1.3 | Work performance data |  | 2.3 | Data representation |  |  |  | 3.3 | Project Management Plan updates
1.4 | Enterprise Environmental Factor |  | 2.4 | Communication skills |  |  |  | 3.4 | Project documents updates
1.5 | Organizational Process assets |  | 2.5 | Interpersonal and team skills
Note on B12: >Business Case
Note on B14: >Contracts >Memorandums of understanding (MOU) >Service Level Agreement (SLA) >Letter of intent >Verbal agreements >email >other writen agreements

## ProgressAnalysis
| Knowledge Area | Project Management Process Groups | [6 empty] | Union Contracts -Constraint Final Status Report -Writen Formal
|  | Initiating Process Group |  | Planning Process Group |  | Executing Process Group | Monitoring and Controlling Process group | Closing Process Group
4 | Project Integration Management | 1. Develop Project Charter | 1 | 2. Develop Project Management Plan |  | 3. Direct and Manage Project Work 4. Manage Project Knowledge | 5. Monitor and Control Project Work 6. Perform Integrated Change Control | 7. Close Project or Phase
5 | Project Scope Management |  |  | 1. Plan Scope Management 2. Collect Requirements 3. Define Scope 4. Create WBS |  |  | 5. Validate Scope 6. Control Scope
6 | Project Schedule Management |  |  | 1. Plan Schedule Management 2. Define Activities 3. Sequence Activities 4. Estimate Activity Durations 5. Develop Schedule |  |  | 6. Control Schedule
7 | Project Cost Management |  |  | 1. Plan Cost Management 2. Estimate Costs 3. Determine Budget |  |  | 4. Control Costs
8 | Project Quality Management |  |  | 1. Plan Quality Management |  | 2. Manage Quality | 3. Control Quality
9 | Project Resource Management |  |  | 1. Plan Resource Management 2. Estimate Activity Resources |  | 3. Aquire Resources 4. Develop Team 5. Manage Team | 6. Control Resources
10 | Project Communications Management |  |  | 1. Plan Communications Management | 1 | 2. Manage Communications | 3. Monitor Communications
11 | Project Risk Management |  |  | 1. Plan Risk Management 2. Identify Risks 3. Perform Qualitative Risk Analysys 4. Peroform Quantitative Risk Analysis 5. Plan Risk Responses |  | 6. Implement Risk Responses | 7. Monitor Risks
12 | Project Procurement Management |  |  | 1. Plan Procurement Management |  | 2. Conduct Procurements | 3. Control Procurements
13 | Project Stakeholder Management | 1. Identify Stakeholders |  | 2. Plan Stakeholder Engagement |  | 3. Manage Stakeholder Engagement | 4. Monitor Stakeholder Engagement

## Questions
Questions | Integration | Scope | Schedule | Cost | Quality | Resources
| Communications | Risk | Procurement | Stakeholder
Project Cost Management
Schedule Variance(SV): how much the project is varying from the schedule as of today
▪ SV>$0 means the project is ahead of schedule (Good: completed more $work than planned) ▪ SV=$0 means the project is on schedule ▪ SV<$0 means the project is behind schedule(Bad: completed less $work than planned or you have planned -$work more than work done as of today)
▪ SV>$800 means you have completed $800 more work than planned as of today ▪ SV=$0 means the project is on schedule as of today ▪ SV<$0 means you have planned to complete $800 more work than you did, as of today
# | Question | Answer | Option-A | Option-B | Option-C | Option-D
1 | The Schedule variance (SV) for your project is +$500. What does this mean? | B | The project is $500 under budget | You have completed $500 more work than planned as of today | There should be $500 more work complete than you have completed as of today | You have spent $500 more than you planned to spent as of today
2 | The Schedule variance (SV) for your project is +$500. What does this mean? | A | This project is ahead of schedule | The project is $500 over budget | The project is under budget | The project is behind the schedule
3 | The Schedule variance (SV) for your project is -$500. What does this mean? | C | You need to complete $500 worth of work to complete the project | The project is $500 over budget | There should be $500 more work complete than you have completed as of today | You have spent $500 more than you planned to spent as of today
4 | The Schedule variance (SV) for your project is -$500. What does this mean? | D | The project is ahead of schedule | The project is $500 over budget | The project is $500 under budget | The project is behind the schedule
Schedule Performace Index(SPI): how quickly the project is progressing compared to the schedule as of today.
▪ SPI >1 means project is ahead of shedule (Good) ▪ SPI = 1 means project is on schedule ▪ SPI < 1 means the project is behind shedule (Bad)
▪ SPI 1.8 means you have completed 80% more work than scheduled(planned) as of today. ▪ SPI 1.0 means the project is on schedule as of today. You have completed 100% of work you planned (scheduled) to complete as of today. ▪ SPI 0.8 means the project is progressing at 80% of the planned rate, as of today. You have completed 80% of what you planned to complete, as of today.
# | Question | Answer | Option-A | Option-B | Option-C | Option-D
1 | The Schedule Performace Index (SPI) for your project is 0.5. What does this mean | D | The project is ahead of schedule | The project is $500 over budget | The project is $500 under budget | The project is behind schedule
2 | The Schedule Performace Index (SPI) for your project is 0.5. What does this mean | C | You need to complete 50% more work to complete the project | The project is $500 over budget | The project is progressing at half the rate expected | you have spent 50% more than you planned to spend as of today
3 | The Schedule Performace Index (SPI) for your project is 1.5. What does this mean | A | The project is ahead of schedule | The project is over budget | The project is under budget | The project is behind schedule
4 | The Schedule Performace Index (SPI) for your project is 1.5. What does this mean | B | The project is 50% under budget | You have completed 50% more work than planned, as of today | There should be 50% more work complete than you have completed as of today | you have spent 50% more than you planned to spend as of today
Cost Variance(CV): how much the project is varying from the budget as of today
▪ CV >$0 means project is under budget (Good) ▪ CV = $0 means project is on budget ▪ CV < $0 means the project is over budget (Bad)
▪ CV = $800 means you spent $800 less than planned, for the work completed as of today. You are running under budget by $800 as of today. ▪ CV=$0 means the project is on budget as of today. ▪ CV= (-)$800 means you spent $800 more than planned, for the work completed as of today. You are running over budget by $800.
# | Question | Answer | Option-A | Option-B | Option-C | Option-D
1 | The cost variance (CV) is -$500. What does this mean | B | The project is ahead of schedule | The project is $500 over budget | The project is $500 under budget | The project is behind schedule
2 | The cost variance (CV) is -$500. What does this mean | B | The project is ahead of schedule | The project is $500 over budget | The project is $500 under budget | The project is behind schedule
Cost Performace Index(CPI): how well the project is performing from a cost standpoint, as of today
▪ CPI >1 means project is under budget (Good) ▪ CPI = 1 means project is on budget ▪ CPI < 1 means the project is over budget (Bad)
▪ CPI 1.8 means you have completed 80% more work, than planned, for the money spent. ▪ CPI 1.0 means the project is on budget. ▪ CPI 0.8 means you have completed 80% of what you planned to complete, with the money spent. [NOTE: 1. CPI does not look at how much money should have been spent as of today 2. CPI looks at how much you spent vs. the work complete]
# | Question | Answer | Option-A | Option-B | Option-C | Option-D
1 | The Cost Performace Index (CPI) for your project is 0.5. What does this mean | B | The project is ahead of schedule | The project is over budget | The project is under budget | The project is behind schedule
2 | The Cost Performace Index (CPI) for your project is 0.5. What does this mean | D | You need to complete 50% more work to complete the project | You have spent 50% more than you planned to spent as of today | You completed only half the work planned to be complete as of today | You completed only half the work planned, based on money spent
3 | The Cost Performace Index (CPI) for your project is 1.5. What does this mean | C | The project is ahead of schedule | The project is over budget | The project is under budget | The project is behind schedule
3 | The Cost Performace Index (CPI) for your project is 1.5. What does this mean | A | You completed 50% more work than planned based on money spent | You have completed 50% more work than planned as of today | You completed only 50% less work than plannedbased on the schedule | You completed only 50% less work than planned based on money spent
Estimate At Completion(EAC): how much we estimate the project will cost in total, based on what we know today
▪ EAC > BAC means we expect the project to overrun the budget (Bad) ▪ EAC = BAC means we expect the project to complete on budget ▪ EAC < BAC means we expect the project to underrun the budget (Good)
▪
# | Question | Answer | Option-A | Option-B | Option-C | Option-D
Variance at Completion(VAC): how much we estimate the project will overrun or underrun, based on what we know today
▪ VAC > $0 means we expect the project to underrun the budget (Good) ▪ VAC = $0 means we expect the project to complete on budget ▪ VAC < $0 means we expect the project to overrun the budget (Bad)
▪
# | Question | Answer | Option-A | Option-B | Option-C | Option-D
Estimate To Complete(ETC): how much more we estimate we need to spend over what we have spent to complete the project
▪
▪
Project Procurement Management
MAKE or BUY decisions ¦¦ RENT or BUY
cost to rent x number of days = cost to buy + (cost to operate*number of days)
# | Question | Answer | Option-A | Option-B | Option-C | Option-D
1 | Rent or Buy
Framework
Framework Practice Test
# | Question | Answer | Option-A | Option-B | Option-C | Option-D
1 | What is an organization that controls project manager, documentation, and policies called? | A | Project Management Office | Tight matrix | Fuctional | Projectized
2 | You are brought into a planning meeting by senior management at your company. They inform you that you have been selected to be the project manager for a new project that will help the company create new product line to be introduced about four years from now. This project is a result of what type of planning? | C | Portfolio planning | Program Planning | Strategic planning | Product life cycle planning
3 | All the following are examples of projects interacting with operations except… | C | Upgrading a factory line with a new computer line | Initiating Go-live phase of a project | Increase output to meet unusually high customer demand | Closing a large sales office
4 | Which of the following is an example of an enterprize environmental factor ? | B | Project life cycle documentation | Stakeholder risk tolerance | Standard performance measurement criteria | Financial, change and risk control procedure
5 | Which of the following is a prioritized order of the project constraint ? | D | Schedule, Risk, Cost | Quality, Schedule, Cost | Scope, schedule, budget | They are all of equal importance unless otherwise stated
6 | Which of the following is an example of a standard? | A | Data transfer rate for thunderbolt 3.0 connections | The number of slides in your last presentation | The shade of paint selected to paint your office | The average speed that someone drives to work
7 | On a large medical buildiing system project, the team is large and communication has been challenge to control. The project expeditor has been used to help with this problem. What is one of the main differences between the project expeditor and the project coordinator? | C | The project expeditor is another title for the project manager | The project expeditor is another title for project coordinator | The project expeditor typically has no decision-making ability | The project expeditor has decision -making ability
8 | What is the main role of functional managers related to projects? | A | To provide subject matter experts(SME) or sevices | To manage project when project manager is not available | To deliver the results of the projects | To manage the project managers
9 | Which of the following is not an organizational culture and style? | D | Accepting the mejority of change requests customer the submits | Working long hours, taking work home, and working weekends | Empowering local managers to make most significant decisions | Focusing most product development on a specific market segment
10 | Which process updates progress and manages changes to the schedule baseline? | A | Control Schedule | Develop shedule management plan | Direct manage project work | Create project management plan
11 | Which of the following uses cross functional work team? | C | A data warehouse practice | An offshore company | A project that utilizes all groups across a company | Union-Approved work places
12 | Which of the following is the most important for the project manager? | B | Controlling Stakeholders | Controlling unneccesary changes | Creating project management plan | Exceeding customer expectations
13 | What is the typical role of senior management on a project? | C | Support the project | Pay for it | Support the project and resolve resource and other conflicts | Resolve resource and other conflicts
14 | A new project just had completed the initiating process group. The planning process group is getting ready to begin. Which process just had been accomplished and which process is getting ready to start? | B | Develop project management plan and direct and manage project work | Identify stakeholders and develop project management plan | Develop project management plan and manage project knowledge | Develop project charter and Direct and manage project execution
15 | Which of the following stakeholders typically "owns" the work of the project when the project is complete? | D | Stakeholders | The project manager | Functional manager | Operations Management
16 | What is the difference between project management life cycle and a project life cycle? | B | The are the same | The Project management life cycle is the project management piece of the project and the project life cycle is the process of completing the the work of the project | The project management life cycle is done in the project and the project life cycle is done after the project is complete | the project management life cycle is the process of completing the work of the project and the project life cycle is the piece of the project management life cycle
17 | The functional manager is planning the billing system replacement project with the newest project manager at the company. In discussing the project, functional manager focuses on the cost associated with running the system after it is created and the number of years the system will last before it must be replaced. What best describes what the functional manager is focussing on? | B | Project Life cycle | Product Life cycle | Project Management Life Cycle | Program management life cycle
18 | What is the ideal project manager function regarding project changes? | B | To delay changes so that the project can be completed | To control unneccesary change | To prevent change control board from seeing anymore change than it is to see | To expedite all change requests to the change control board
19 | What is created in the initiating process group? | D | Project charter and requirement documentations | Project scope statement and various management plans | Project charter and project knowledge | Project charter and stakeholder register
20 | A business analyst has a career path that has been very important to her throughout the ten years of her career. She is put on a very important project with with a strong metrix organizational structure. Which of the following is likely viewed as the most serious drawback of being on the project? | A | Being away from the group might make career advancement in the department more difficult | Working with people who have similar skills | Working long hours because the project is a high priority | Not being able to take BAP certification test because she will be so busy
21 | Which of the following is the definition of the program management? | A | Managing related or similar projects in a coordinated way | The process of computer program management | Managing a television program | Done for a purpose
22 | Who is accountable for creating and executing project management plan? | D | The team | The company that was awarded the outsourcing contract | The project manager and the project management team | The project manager
23 | What are the five process groups used in the project management institute, Inc. aproach to project management? | A | Initiating, Planning, Executing, Monitoring and controlling, Closing | initiating, planning, executing, testing, sign-off | Requirements, system development, testing, UAT, sign off | Initiating, planning, executing, testing, closure
24 | Which of the following is an advantage of projectized organization? | B | Business unit competency | Optimization for a single focus on the project | Having to get approval from functional management | A place to go when project is complete
25 | What is the name of the comprehensive document created during planning process group? | C | Project charter | Project scope statement | Project management plan | A signed contract
26 | Which of the following best describes a stakeholder in a project? | D | A team member | The project manager | Someone who works in an area impacted by the work of the project | All the answer
27 | The data warehouse project is about halfway complete at a mejor retail client. Your company is doing the implementation and has 12 team members at various locations across three different buildings. Communication and team building has been a real challenge. Which of the following would fix or improve the problem? | B | Changing the organization to function structure | Colocation | Replacing the project manager | Hiring project coordinators
28 | The project management life cycle is similar to which of the following? | C | Project life cycle | SDLC | Plan-do-check-act | Use case analysis
29 | Which of the following is not a regulation? | C | The building code for a city | The documented way to dispose of old computers | The average speed on a street in a day | The zoning for an area
30 | Which of the following is an advantage of a functional organization? | A | Having a home to go when the project is complete | Not having a home when the project is complete | Having more than one project to work on | Having more than one boss
Go | Stakeholders
Project Stakeholders management
# | Question | Answer | Option-A | Option-B | Option-C | Option-D
1 | During which process is the project manager most likely to increase support and minimize resistance from stakeholder? | C | Identify Stakeholders | Plan stake holder management | Manage stake holder engagement | Control stakeholders engagement
2 | Vel electrical has won the contract to install wireless netowrking in Indoor stadium. This is very complex contract because there are numbers of stakeholders are involved: The owner of the stadium, various companies associated with the owner and the city of Kolkata. What document will be most effective for organizing the stakeholders | A | Stakeholder register | Stakeholder engagement plan | Issue log | Charter
3 | All of the followings are descriptions derived from analytical techniques used in stakeholders management except.. | A | Nonregistant | Neutral | Supportive | Leading
4 | The marketing brochure redesign project is entering the manage stakeholder engagement process. To effectively manage stakeholder engagement, the project manager has a variety of tools and techniques available during this process. What are they? | A | Interpersonal and team skills, communication feedback, and ground rule | Communications methods, alternative analysis, and management skills | Communications skills, Communication management plan and management skill | Product analysis, Communications methods, and management skills
5 | Sam is running a project to upgrade a client's website to a new framework. Expectation management has been very challenging on this project. Sam has had challenges keeping the main sponsor involved as the project has evolved. Currently, Sam is managing stakeholder management. Which of the following best describes what he will create? | A | Updates to the stakeholder engagement plan, change log, and issue log | Aprove change requests, and updated stakeholder registry | Resolved Issues and approved change requests | Updated stakeholder registry, resolved issues, and change requests
6 | The project to update the retail store to accommodate the new video game platform is ready for initial planning. Stakeholders have been identified. What documentation will be created as a result of identification? | A | Stakeholder register | Stakeholder management plan | Issue log | Charter
7 | All of the following interpersonal or soft skills are applicable to managing stakeholder engagement except… | C | Building trust | Resolving conflict | Passive listening | Overcoming registance to change
8 | During the plan stakeholder engagement process for the accounting system upgrade project, what tools and techniques are available to the project manager? | B | issue logs, stakeholder analysis, reporting systems, and approved change requests | Expert Judgement, meetings, and mind mapping | Management skills, communications methods, stakeholder analysis, and interpersonal skills | Stakeholder analysis, issue logs, and approved change requests
9 | Which processes does the project manager use to manage the project stakeholders? | B | Plant stakeholder engagement, manage stakeholder engagement, monitor stakeholder engagement | Identify stakeholder s, plan stakeholders engagement, manage stakeholder engagement, monitor stakeholder engagement | Identify stakeholders, plan stakeholder engagement, monitor stakeholder engagement | Identify stakeholders, plan stakeholder engagement, manage stakeholder engagement
10 | During identify stakeholder process, the project manager of the security project has what key tools & techniques to his disposal? | D | Stakeholder analysis, stakeholder management strategy chart, and expert judgement | Power/ Interest grid, stakeholder analysis, and expert judgement | Stakeholder management strategy chart, stakeholder analysis, power/interest grid, and expert judgement | Expert Judgement and stakeholder analysis
11 | To effectively manage stake holders to increase support for and minimize negative impact to a project, project managers often rely on strategy tools during identify stakeholder process. A key tool is the analysis matrix. Of the following, which best represents typical matrix entries? | C | Level of impact on the project, strategy to gain support or minimize negative impact, stakeholder name, level of interest in the project, requirements for level of communication | Level of interest in a project, stakeholder name, political influence within the organization, strategies to gain support or minimize negative impact | Strategies to gain support or minimize negative impact, level of interest in the project, stakeholder name, level of impact on the project | requirements for level of communication, stakeholder name,level of interest in the project,political influence within the organization,Strategies to gain support or minimize negative impact
12 | The chief financial officer of the mortgage banking has been reassigned to the IT department and will have no further involvement in the financial department, which of the following documents should be updated for the Tax laws Accounting upgrade project? | C | Stateholder register, | Power/Interest grid | Stakeholder register and power/interest grid | issue log
13
14
15
16
17
18
19
20
21
22
23